Attendees: Jesse Bolinger, Michael Hruska, Sarah Baebler-Hall, Ashley West, Charla Schmid, Michelle Lents

The agenda is as follows:

- Call to Order

- Minutes

- Agenda Approval

- Introduction of Executive Assistant Amanda McVann

  - Skipped for this meeting

- Center Accessibility Updates

  - Michael:

    - Currently compiling report from what was found in the accessibility study

    - Few updates:

      - Changing accessibility bathroom from front entrance to women’s bathroom by the back-accessibility entrance

        - Will be cost-effective way to reduce cost

        - Bathroom must be checked for a drain and the angle of the drain to make sure it is in compliance

    - Minor changes from the study:

      - Lines must be repainted

        - One space was not six-inches in compliance, but may be in compliance once repainted

      - Jesse: try to see if it’s possible to bring a guide-dog or wheelchair through it

        - Michael: can schedule some time to do that

      - Other signs need to be put up and will consult with Sarah about that

    - Blind/Visually-Impaired:

      - Sarah met with career planners and went through programmatic accessibility

        - None of the software is updated and needs to be updated

      - Sarah:

        - Brian Dennis is working on the screen reader/mag. for the computers on the state level. How does that affect our timeline for getting things done?

      - Have fliers that are in an accessible digital format

      - Magnifier and screen reader was not working and accessible despite being on the computer

- Old Business

  - One Stop Certification Accessibility Standards

    - Ashley: we are probably going to be a month behind

      - Evaluation will most likely take place the end of January/beginning of February

      - Complete self-assessment six-months ahead of time before the evaluation (suggestion by the state)

      - Evaluate and fill any gaps prior to the evaluation

      - Needs:

        - Referral form (Ashley is currently working on)

        - Address gaps for physical and programmatic accessibility from study

          - Try to submit within the next week in order to schedule a time to meet with the Core Partners to address the gaps

- Public Comment

  - NO NEW BUSINESS

- Establish Next Meeting

  - Wednesday, December 7th 2022 @ 9 AM via Zoom

- Adjournment

Action Items:

- Michael & Jesse need to schedule time to see if the space is guide-dog or wheelchair compliant

  - Tuesday or Wednesday afternoon is best

- Upcoming meetings:

  - Wednesday, December 7th 2022 @ 9 AM via Zoom