## Slide 1: LWDA Leadership Office Hours

## Slide 2: Today’s Presenter
Michelle McNertney
  michelle.mcnertney@iwd.iowa.gov

## Slide 3: Purpose of Office Hours
To provide an opportunity for LWDA Leadership (CEOs, LWDB Directors, Staff to the Board) to
  Ask questions and seek clarification regarding their tasks within the Iowa workforce system transformation
  Engage in dialogue with other LWDA Leadership and Iowa Workforce Development
To provide an opportunity for Iowa Workforce Development to
  Provide guidance or explanation on policies

## Slide 4: Objectives of Office Hours
Updates:
  Local Area Performance Negotiations Update
  One-Stop Operator Update
  Local Plan Guidance
  PY20 Monitoring
Communication Plan
Onboarding new CEOs

## Slide 5: LWDA Leadership Key Deliverables/ Revised Timeline - Updated
Task | Deadline | Responsible Party
Select direct service provider using competitive procurement process | 12/31/2020 | LWDB
Select One-Stop Operator using competitive procurement process | ?? | LWDB
Complete Local Area Performance Negotiations | ?? | LWDB
Complete Local Plan | 1/1/2022 | LWDB*
Develop and approve LWDB budget for PY21 (7/1/21 – 6/30/22) | 5/15/2021 | LWDB*
Execute contract extensions/modifications for Title I Service Providers for 7/1/2021 or complete new RFP for Title I Service Provider effective 7/1/2021 | 6/30/2021 | LWDB*
*Requires final approval from CLEO |  | 

## Slide 6: Updates

## Slide 7: Updates
Local Area Performance Negotiations
  Tentatively scheduled for February 2021
  Working with U.S. DOL to push back
One-Stop Operator Procurement
  U.S. DOL recently provided T.A. to R5 states
  OSO must be selected through competitive procurement, but does not have to be RFP
  IWD working on guidance for Local Areas

## Slide 8: Updates
Local Plan Guidance
  Guidance will be available from Core Partners in January 2021, includes template and training
  Due date will be January 1, 2022
  Continue to reference old plans until new plan is approved
PY20 Monitoring
  PY20 Programmatic Monitoring has begun
  Monitoring tools/documents will be sent to all boards soon

## Slide 9: Communication Plan

## Slide 10: WIOA Governance Structure
US Department of Labor
State Governor
State Workforce Development Board
State Workforce Agency
Chief Elected Official
Local Workforce Development Board
One-Stop Delivery System
Appointment Consultation
Appointment Partnership Approvals
Vision Oversight
Guidance
Oversight
Appointment
Funding Oversight
Compliance Funding
Funding
Consultation
Consultation
Joint Oversight
Funding

## Slide 11: Local Workforce System Oversight Options
Chief Lead Elected Official (CLEO)
Local Workforce Development Board (LWDB)
Appointment
Selection
Joint Selection &
Oversight
Joint Oversight
Board Staff
Selection & Oversight
Fiscal Agent
Service Providers
(Adults, Dislocated Workers, Youth)
One Stop Operator
Option for LWDB to serve in this role with approval from CEO and State Governor
Option for LWDB to serve in this role with approval from CEO and State Governor, with Youth services provided by a separate entity
Provided by a Separate Entity or Grant Sub-Recipient
Provided by a Separate Entity or Grant Sub-Recipient

## Slide 12: Communication Protocol
IWD
Local Workforce Development Board
and/ or LWDB staff
Fiscal Agent
Service Provider
One Stop Operator
Direct contractual relationship
Notes: The Fiscal Agents receive contracts from IWD on behalf of the local workforce development areas. Therefore, IWD has a contractual relationship with Fiscal Agents that it does not have with One Stop Operators or Service Providers. However, any communication by IWD with Fiscal Agents will be with regard to fiscal management and operations and will also include a cc to the LWDB Executive Director.

## Slide 13: Onboarding for new CEOs

## Slide 14: Onboarding for new CEOs
Training for CEOs new to Workforce Development will be a two-pronged approach
  Information from IWD
  Information from the Local Workforce Development Board (LWDB)
February 2021
Thoughts to make training effective?

## Slide 15: Questions?

## Slide 16: Contact
      WIOAgovernance@iwd.iowa.gov
      michelle.mcnertney@iwd.iowa.gov
      linda.rouse@iwd.iowa.gov
      michael.witt@iwd.iowa.gov

## Slide 17: Next Office Hours
Friday, January 8th
12:00 pm

## Slide 18: Thank You!